WV FEMA Mapping Partners

Conference Call- 8/7/2006

Attendees:

Melissa Aguglia:

Robert Perry

Jason Roberts

Craig Neidig

Katherine Paybins

Janette Bennett

Todd Miller

Updates:

- Mike Craghan has left FEMA, and has not been replaced yet.  In the meantime we can contact Jon Janowicz or Nikki Roberts.

- Regarding the Mid-Course Correction for Map Mod, a rumor has been circulating that some of the work may re-bid to parties other than Baker.

- Kanawha and Putnam are scheduled for completion by Baker in August, but there has been no specific communication yet.

- Progress is being made on Wayne County, mostly through conversion, with some updates (such as Spring Valley, which flooded recently but is not a mapped flood hazard area).

- Robert reported that Ohio County is done, and Raleigh County becomes effective Sept. 29.

- Robert says 6 counties are scheduled for completion in 2006, 7 in 2007, and that some counties scheduled for 2003-5 are waiting to be finalized.  So there are about 30 counties “up and running” right now, and about 40 counties left.

- 2008 is scheduled to be the last year for Map Mod, but that may be pushed back a year in some states (for example, PA stopped all Map Mod until they get LiDAR).

- Jason reported that Fayette and Summers Counties are wrapping up, and they are getting started on Webster.

- Todd reported that CVI is completing the DFIRM update for Gilmer County and will begin gathering LiDAR data for Preston County this year, and will work with Robert on some education/outreach activities in Preston and statewide over the next two years.

- Regarding roads data, Craig explained that the WV SAMB roads geometry will be released for reference use, but that it is not an addressed data layer, there are no attributes and it has not been field-checked.  He thought we should not look for the final version any time soon… maybe after the end of the year.   County 911 Directors may be able to provide road names.  For example, the field work has been done in Preston County so the 911 Director should have that information.  Craig also explained that WVDOT is compiling SAMB data with their own road attributes for roadway management (recording accidents, etc).  Sean Litteral had intended to explain the WVDOT roads data today on the conference call, but could not attend.

- Regarding the long-ago proposed letter to release liability for use of SAMB Hydro data, it seems that is no longer a top concern, but Craig (or Todd) will follow-up with Jon Janowicz on the status of that.

- There was some discussion at some point (I don’t have notes on this) about the utility of the WV SAMB  3M DEM for Approximate A Zone redelineation.  According to Robert, Mike Craghan had said something about the 3M data not being suitable for that use because the data is not completely uniform across the state.  However, the consensus seemed to be that the 3M DEM is the most uniform, precise and up-to-date topo information available, and that it ought to be put to use.  CVI plans to use the data for eventual A Zone refinement in Preston County, so Todd (working with Robert) can bring this up with Jon Janowicz.

- Todd asked if others would rather facilitate the calls, and there were no takers.

- The next conference call was set for Monday October 2 at 11 AM.

Action items:

- Todd: Ask Jon Janowicz about use of 3M SAMB DEM for A-Zone Refinement

- Kurt: Follow-up with Roger Cotrell at Watershed Concepts regarding the above (left over from June 05 Conference Call… and Kurt has sent a request to Watershed for that info)

- Craig (or Todd): Follow-up with Janowicz on the status of the liability release for the Hydro data.

Since the call, Eric Hopkins sent me Kurt’s new email:  kdonalds@wvu.edu