WV View Strategic Plan 2005

| Area/Goal | 1 Year (2005/2006) (Goals that are concrete) | 5 Year (2005/2010) (Goals that are broad, general) |
| --- | --- | --- |
| 1 Consortium Development |  |  |
| Outreach to new partners | Add total of 2 new educational partners (Glenville, Marshall - done) Add 1 new non-profit partner (Skytruth - done) Add one state or federal partner (NASA, USDA / USFS Northeastern Area State and Private Forestry Field Office – done) | WV View to include all remote sensing related institutions in the state Grow the number of institutions offering undergraduate remote sensing |
| Consortium management | Full-time manager (done) | WV View run by a part time manager, balance of manager’s time spent on research & related grants that link to partners’ missions |
| 2 Archive Development |  |  |
| Website structure | Develop new educational section for website (done) Basic GLOVIS implementation (on hold) | WV View website is acknowledged as the primary remote sensing archive for the state |
| Data sets | Add recent TM Landsat images (in process) Add selected lidar data, historical air photos (on hold) | Purchase an annual TM or equivalent data set Grow to include a significant number of data other than TM, such as lidar, historical air photos, MSS, ASTER, MODIS, etc |
| 3 Education, Outreach, & Training |  |  |
| Higher Ed Remote sensing courses | WV-Sponsored support for laboratory coursework at Marshall University (Imagine licenses – done) | Establish new remote sensing courses at undergrad institutions |
| Educational resources | Remote sensing software for educational partners (Glenville State – done) | Remote sensing software for educational partners Lab and lecture resources available |
| Student RS research grants | Award 3 research grants annually (in process) | Award multiple research/scholarship grants annually: Graduate & Undergraduate |
| RS Conference |  | Appalachian RS conference every 2 years |
| Website | Add educational links to website (done) | WV View website is regularly updated with RS educational information; is a major resource for educators |
| 4 Research |  |  |
| Student RS research grants | Award 3 research grants annually (in process) | Award multiple research/scholarship grants annually: Graduate & Undergraduate |
| Faculty research grants |  | Award grants to support faculty research |
| 5 Applications Development & Technology Transfer |  |  |
| Technology resource | Develop links with State GIS office (To be started) | Become the remote sensing technology and science resource in West Virginia |
| Develop links to industry and applied users | Add additional applied federal or industry partner (USDA / USFS Northeastern Area State and Private Forestry Field Office – done) Develop list of potential industry WV View partners (To be started) | Develop applications program that is linked to mission of partners |